## Overal Plan
Project Name |  |  |  | GraduationProjectMS
Client Name |  |  |  | Dung Cu Viet
Project Manager |  |  |  | Van Tran Thao
Created by |  |  |  | Van Tran Thao
| ID | On sprint | Name | Start date | End date | Week lasting
| PB0 |  | Kick-off week | 13/02 | 19/02
| PB1 | sprint 1 | Đăng nhập (Step 0) | 20/02 | 26/02 | 1
| PB2 |  | Liên hệ GV (Step 1) | 27/02 | 2023-12-03 | 2
| PB3 | sprint 2 | Xét giao (Step 2) | 13/03 | 26/03 | 2
| PB4 |  | Đề cương (Step 3) | 27/03 | 2023-02-04 | 1
| PB5 | sprint 3 | Đề cương 2 (Step 4) | 03/04 | 23/04 | 3
| PB6 | sprint 4 | Thực hiện HPTN (Step 5) | 24/04 | 2023-07-05 | 2
| PB7 | sprint 5 (end) | Bảo vệ + Kết quả (Step 6) | 2023-08-05 | 14/05 | 1

## Gantt
Project Name
Client Name
Project Manager
Created by
WBS Number | Task Title | % of Task Completed |  |  | Kick-off | [6 empty] | Sprint 1: Đăng nhập | [6 empty] | Sprint 1: Liên hệ gv | [6 empty] | Sprint 1: Liên hệ gv | [6 empty] | Sprint 2: Xét giao | [6 empty] | Sprint 2: Xét giao | [6 empty] | Sprint 2: Đề cương (1) | [6 empty] | Sprint 3: Đề cương (2) | [6 empty] | Sprint 3: Đề cương (2) | [6 empty] | Sprint 3: Đề cương (2) | [6 empty] | Sprint 4: Thực hiện HPTN | [6 empty] | Sprint 4: Thực hiện HPTN | [6 empty] | Sprint 5:Bảo vệ + Kết quả
[5 empty] | WEEK 0 (13/2/2023) | [6 empty] | WEEK 1 (20/2/2023) | [6 empty] | WEEK 2 (27/02/2023) | [6 empty] | WEEK 3 (06/03/2023) | [6 empty] | WEEK 1 (13/03/2023) | [6 empty] | WEEK 2 (20/03/2023) | [6 empty] | WEEK 3 (27/03/2023) | [6 empty] | WEEK 1 (03/04/2023) | [6 empty] | WEEK 2 (10/04/2023) | [6 empty] | WEEK 3 (17/04/2023) | [6 empty] | WEEK 1 (24/04/2023) | [6 empty] | WEEK 2 (01/05/2023) | [6 empty] | WEEK 1 (08/05/2023)
|  |  | 11 | 12 | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
0 | Discovery |  |  |  | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 |  |  | 2021-07-29 | 2021-07-30 | 2021-07-31 | 2021-08-01 | 2021-08-02 |  |  | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 |  |  | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 |  |  | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11
1.1 | Kickoff Call + Agenda | 100% |  |  | zz | zz | 2022-06-29 | 2022-06-30 | 2022-07-01 |  |  | 2022-07-11 | 2022-07-12 | 2022-07-13 | 2022-07-14 | 2022-07-15 |  |  | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 |  |  | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 |  |  | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09
1.2 | Project Plan | 60% |  |  |  | zz | zz | [11 empty] | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 |  |  | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 |  |  | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09
1.3 | Internal Project analysis | 100% |  |  |  |  | zz | zz | 2022-07-01 | [9 empty] | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 |  |  | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 |  |  | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09
1.4 | DOCUMENTs | [6 empty] | zz | zz | zz | zz
| Agenda + General Process | 100% | [6 empty] | zz | zz | zz
| General Requirements | 70% | [7 empty] | zz | zz
| Members' roles assigning | 100% | [8 empty] | xf
1 | Sprint 1 |  |  |  | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 |  |  | 2021-07-29 | 2021-07-30 | 2021-07-31 | 2021-08-01 | 2021-08-02 |  |  | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 |  |  | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 |  |  | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11
1.1 | Research + Analysts | 100% | [9 empty] | xf | xf | [5 empty] | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 |  |  | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 |  |  | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09
| PB1: Đăng nhập | 100% | [9 empty] | xf | xf
| PB2: Liên hệ GV | 100% | [16 empty] | xf | xf | xf
1.2 | Design | 100% | [11 empty] | xf | xf | xf
| UI/UX | 100% | [11 empty] | xf | xf
| PB1: Đăng nhập | [12 empty] | xf | xf
PB2: Liên hệ GV
| Diagrams | 100% | [11 empty] | xf | xf | xf
| PB1: Đăng nhập | [12 empty] | xf | xf | xf
PB2: Liên hệ GV
1.3 | Development | 100%
| PB1: BE | 100% | [13 empty] | xf | xf
| PB1: API | 100% | [12 empty] | xf | xf | xf
| PB1: FE | 100% | [12 empty] | xf | xf | xf
| PB2: API | [21 empty] | xf | xf
| PB2: FE | [20 empty] | xf | xf | xf
| PB2: BE | [20 empty] | xf | xf | xf
1.4 | Testing | 100% | [13 empty] | xf | xf | xf |  | 2022-08-01 | 2022-08-02 |  |  |  |  | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 |  |  | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09
| Test case Document | [14 empty] | xf | xf | xf
PB1: Đăng nhập
PB2: Liên hệ GV
| Test Proceed | [15 empty] | xf | xf
| PB1: Đăng nhập | [15 empty] | xf | xf
PB2: Liên hệ GV
1.5 | Deploy | 100% | [14 empty] | xf | xf |  | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 |  |  | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 |  |  | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09
| PB1: Đăng nhập | [15 empty] | xf | xf
PB2: Liên hệ GV
1.6 | User Manual Document | [15 empty] | xf | xf |  | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 |  |  | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 |  |  | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09
| PB1: Đăng nhập | [15 empty] | xf | xf
PB2: Liên hệ GV
2 | Sprint 2
2.1 | Research + Analysts | [17 empty] | 2022-08-05 | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 |  |  | 2022-08-19 | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 |  |  | 2022-09-09
2.2 | Design
UI/UX
Diagrams
2.3 | Development
2.4 | Testing
Test case Document
Test Proceed
2.5 | Deploy
2.6 | User Manual Document
3 | Sprint 3
3.1 | Research + Analysts
3.2 | Design
UI/UX
Diagrams
3.3 | Development
3.4 | Testing
Test case Document
Test Proceed
3.5 | Deploy
3.6 | User Manual Document
4 | Sprint 4
4.1 | Research + Analysts
4.2 | Design
UI/UX
Diagrams
4.3 | Development
4.4 | Testing
Test case Document
Test Proceed
4.5 | Deploy
4.6 | User Manual Document
5 | Sprint 5
5.1 | Research + Analysts
5.2 | Design
UI/UX
| Diagrams | [17 empty] | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 |  |  | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19
5.3 | Development | [17 empty] | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 |  |  | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19
[19 empty] | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 |  |  | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19
5.4 | Testing
Test case Document
| Test Proceed | [17 empty] | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 |  |  | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19
5.5 | Deploy
5.6 | User Manual Document

## Story Points
Points | Hour
1 | 7 days
3 | 21 days
5 | 25 days
7 | >40 days
| ID | On sprint | Name | Start date | End date | Week lasting
| PB0 |  | Kick-off week | 13/02 | 19/02
| PB1 | sprint 1 | Đăng nhập (Step 0) | 20/02 | 26/02 | 1
| PB2 |  | Liên hệ GV (Step 1) | 27/02 | 2023-12-03 | 2
| PB3 | sprint 2 | Xét giao (Step 2) | 13/03 | 26/03 | 2
| PB4 |  | Đề cương (Step 3) | 27/03 | 2023-02-04 | 1
| PB5 | sprint 3 | Đề cương 2 (Step 4) | 03/04 | 23/04 | 3
| PB6 | sprint 4 | Thực hiện HPTN (Step 5) | 24/04 | 2023-07-05 | 2
| PB7 | sprint 5 (end) | Bảo vệ + Kết quả (Step 6) | 2023-08-05 | 14/05 | 1